# Methane Detection Work Split and Timeline

Five person project coordination plan  October 7 to November 10 2026

# 1 Executive summary and operational constraints

The team will build a reproducible satellite methane detection research pipeline. The baseline is the non-negotiable core: accessible data, a documented split, a working reader, a trained or executable baseline, and evaluation artifacts. Wind-aware learning, weak-plume curriculum learning, cross-sensor transfer, and emission quantification are advanced experiments that proceed only when their required data and interfaces have been confirmed.

| Operating constraint | Team rule |
| --- | --- |
| Team structure | One Team Leader plus Members 1 to 4. Each major module has one accountable owner; the Leader reviews and integrates. |
| Active phases | Oct 7 to Oct 23 and Nov 2 to Nov 10, 2026. |
| Planned break | Oct 24 to Nov 1. No active development; work must be committed, indexed, and handed over before the break. |
| Scope control | A functioning baseline precedes any claim of improvement or advanced model. |
| Research integrity | No invented results, schema, access status, hardware assumption, or novelty claim. |
| Collaboration | Private shared Git repository; branch, Pull Request, review, test, and handover are required for merge. |
| Practical default | CPU-compatible smoke tests; optional GPU runs only if the team has verified access. Large raw data remains outside Git with documented acquisition steps. |

# 1.1 Team ownership

| Owner | Role | Primary deliverable | Reviewer |
| --- | --- | --- | --- |
| Team Leader | Integration and Research Coordinator | Decision log, milestones, interfaces, final integration, report and presentation | Whole team |
| Member 1 | Data and Geospatial Lead | Dataset inventory, manifest, reader, preprocessing, split and QC report | Leader and Member 2 |
| Member 2 | Baseline Model and Training Lead | Baseline model, training configuration, checkpoints, predictions | Member 4 and Leader |
| Member 3 | Methodology and Robustness Lead | Wind or weak-plume experiment, ablation, failure analysis | Member 2 and Leader |
| Member 4 | Evaluation Quantification and Demonstration Lead | Metrics, figures, error analysis, optional quantification, demo app | Leader and Member 1 |

# 2 Master timeline and milestone matrix

| Date | Active owner(s) | Main task and dependency | Deliverable and acceptance criterion |
| --- | --- | --- | --- |
| Oct 7 | Leader; M1; M2 | Repository, task board, candidate data inventory, environment smoke test. No dependencies. | Repo policy and README exist; one toy or verified-sample smoke test passes. |
| Oct 8 | Leader; M1; M2 | Dataset access and licence verification; reproducibility utilities. | Inventory distinguishes verified access from open questions; seeds/config/checkpoint test works. |
| Oct 9 | M1; M2; Leader | Open real samples; start canonical reader; setup review. | At least one sample opens with metadata and an initial reader contract is documented. |
| Oct 10 Milestone | All | Data feasibility review and role checkpoint. | Primary dataset candidate, schema evidence, and risk log are approved; no unverified source fields are assumed. |
| Oct 11 | M1; M4 | Preprocessing, label overlays, metrics unit tests. | Ten visual checks and hand-checked metric tests saved. |
| Oct 12 | M1; M4 | Split policy, data QC, evaluator interface. | Scene-aware or documented split policy committed; metric API ready. |
| Oct 13 | M2; M3 | Baseline implementation begins; advanced-method feasibility plan begins. | Tiny-subset overfit works or is documented as blocked; methodology plan names prerequisites. |
| Oct 14 | M2; M1 | Baseline training configuration and data fixes. | Config, model input, loss, and checkpoint convention agree with reader contract. |
| Oct 15 | M2; M4 | First full baseline run and evaluator connection. | Saved predictions can be scored by the independent evaluator. |
| Oct 16 Milestone | Leader; all | Baseline readiness and scope lock. | Working baseline path or a documented data blocker; fixed split; approved one advanced experiment or fallback. |
| Oct 17 | M2; M3; M4 | Baseline rerun/error catalogue; advanced implementation; report skeleton. | Baseline failure examples and controlled advanced config exist. |
| Oct 18 | M1; M3 | Wind/difficulty metadata verification; advanced experiment continuation. | Required metadata is verified or the experiment is reduced to its fallback. |
| Oct 19 | M2; M3 | Controlled comparison run. | Baseline and proposed run share split, evaluator, and configuration record. |
| Oct 20 | M4; Leader | Error analysis, metrics review, dashboard mock integration. | False-positive/negative gallery and run-ID traceability available. |
| Oct 21 | All | Integration rehearsal and unfinished-task triage. | Fresh clone can run unit tests and one saved report or inference command. |
| Oct 22 | All | Documentation, checkpoint index, handover preparation. | Each member has commits, artifacts, known issues, and next steps ready. |
| Oct 23 Milestone | All led by Leader | Phase 1 freeze. | Clean main, phase1_handover.md, run/checkpoint index, restart checklist, and exact November priorities are complete. |
| Oct 24 to Nov 1 | No active development | Planned break. | No work scheduled; repository, data instructions, checkpoints, and handover remain backed up. |
| Nov 2 | All led by Leader | Restart, integration and blocker review. | Environment, reader, evaluator, baseline inference, and report command rerun successfully or have an assigned blocker. |
| Nov 3 | M2; M3; M4 | Advanced comparison; cross-sensor or quantification feasibility check. | One fair comparison runs or a no-go limitation is documented. |
| Nov 4 | M2; M3; M4 | Ablation and final prediction generation. | Paired baseline/proposed result folders and configuration diffs saved. |
| Nov 5 Milestone | Leader; all | Evidence review. | Measured results, limitations, final figures list, and unresolved risks are approved. |
| Nov 6 | M4; M1; M3 | Final metrics, error analysis, optional validated quantification. | Every displayed metric has a run ID, split, and clear units/assumptions. |
| Nov 7 | M4; Leader | Dashboard or demonstration and report drafting. | Demo renders saved outputs; report distinguishes evidence, target, and limitation. |
| Nov 8 Milestone | All | End-to-end integration and rehearsal. | Clean-clone walkthrough works; project is 80% presentation-ready with a ranked fix list. |
| Nov 9 | All | Fixes, report, slides, and final rehearsal. | No unsupported claim remains; demo script and backup screenshots are ready. |
| Nov 10 Milestone | All | Final submission and presentation. | Reproducible end-to-end pipeline, defensible evaluation, documented limitations, report, slides, and demonstration complete. |

# 3 Individual workload and completion criteria

| Owner | Active dates | Responsibilities | Completion evidence | Dependencies and risks |
| --- | --- | --- | --- | --- |
| Team Leader | Oct 7–23; Nov 2–10 | Own task board, decisions, reviews, integration, blocker handling, and final narrative. | Daily stand-up notes; milestone reports Oct 10, 16, 23, Nov 5, 8, 10; final integration log. | Needs artifacts from all owners. Risk: taking over member tasks. Mitigation: approve interfaces and unblock, then return ownership. |
| Member 1 | Oct 7–23; Nov 2–6 | Own access verification, data manifest, preprocessing, splits, label and geospatial QC, wind/units checks. | Reader, manifest, data card, split files, visual QC gallery, data handover. | Enables all model work. Risk: unavailable data/schema. Mitigation: escalate by Oct 10 and nominate a verified fallback dataset. |
| Member 2 | Oct 7–23; Nov 2–5 | Own baseline model, training loop, checkpoints, inference, and reproducibility. | Baseline config, smoke test, saved runs, prediction folders, model card. | Depends on M1 data contract and M4 metrics. Risk: model fails to learn. Mitigation: tiny-subset overfit, simpler architecture, inspect masks. |
| Member 3 | Oct 13–23; Nov 2–6 | Own one advanced research experiment and ablation. | Methodology plan, advanced module/config, controlled comparison, failure analysis. | Depends on stable baseline plus verified wind/difficulty fields. Risk: unsupported data or compute. Mitigation: defined no-go and error-analysis fallback. |
| Member 4 | Oct 11–23; Nov 2–10 | Own independent evaluation, figures, cross-sensor/quantification feasibility, demo, and reporting evidence. | Metric tests, figures, error gallery, report generator, optional app, reproducibility report. | Depends on M1 metadata and M2/3 predictions. Risk: invalid metric/units. Mitigation: hand-checked tests and explicit assumption log. |

# 4 Shared data contracts and integration requirements

The following are internal contracts proposed for the project. Member 1 must confirm or revise them against downloaded data before they become binding.

| Artifact | Required fields | Contract rule |
| --- | --- | --- |
| Manifest row | sample_id, dataset_name, split, file reference, label reference if present, sensor, preprocess_version | No training code reads untracked ad hoc files. |
| Canonical sample | image, target or null, metadata, transforms | Image type/shape and target semantics must be documented; no assumed native schema. |
| Run folder | config, seed, code commit, checkpoint pointer, metrics, predictions, logs | A reported result without a run folder is not presentation evidence. |
| Prediction record | sample_id, probability or score, mask if applicable, threshold, run_id | Evaluator joins by sample_id only; never rely on row order. |
| Evaluation report | dataset, split, metric, sample count, exclusions, output path | State whether each result is measured, literature-reported, or a target. |
| Quantification record | sample_id, source-rate target if verified, predicted rate, unit, wind assumption, uncertainty note | Only permitted when valid target and units are confirmed. |

# 5 Daily leadership checklist and blocker escalation

| Time | Leader action | Evidence |
| --- | --- | --- |
| Start of day | Confirm each owner has one task, one expected artifact, and one dependency status. | Task board updated. |
| Midday | Ask for a screenshot, command output, or artifact link; identify blockers early. | Short stand-up note. |
| Before merge | Check branch, tests, configuration, run ID, and handover note. | Pull Request checklist. |
| End of day | Update green/amber/red status, assign unresolved blockers, and set next-day dependency order. | daily_handover.md entry. |

Escalation rule: a blocker that prevents a task for more than one working day must be logged with category, evidence, owner, fallback, and decision deadline. Dataset access and schema blockers escalate immediately because they affect every downstream module.

# 6 Handover and quality gates

Start from main, pull the latest version, and create feat/<date>-<component>.

Work only inside the agreed module boundary unless a reviewed interface change is required.

Before Pull Request: run relevant tests, save config and run ID, update documentation, and add at least one verification statement.

The Pull Request description must include: what changed, how it was verified, configuration/data impact, known issues, and next dependent task.

The Leader or named reviewer checks integration impact before merge.

By Oct 23, every owner must deliver the handover record below.

## 6.1 Phase 1 handover template

Owner: Completed work and merged branch or PR: Files/modules owned: Dataset and split status: Run IDs, checkpoints, metrics, and what each number means: Exact commands to reproduce: Known issues and failed attempts: Next smallest November task: Dependencies or decisions needed from the Leader:

## 6.2 Final integration checklist

Clean checkout installs documented dependencies and runs the smoke test.

Manifest and split policy are present; raw data is not committed.

Baseline checkpoint or deterministic report path is available.

Predictions, metrics, configurations, and figures trace back to a run ID.

Advanced method uses a fair baseline comparison or is reported as a scoped limitation.